## NSF_Supported
Example Budget Sheet for a NSF Support Project
Note: Please add 58.5% overhead charge for the University of Texas at Austin
Last updated: December 15, 2020
Project description:
A NSF supported project using T-Rex and Instrumentation Van at a site 1000 miles from Austin for seismic prospecting study.
(700 miles + 300 miles from site to site (5 sites total))
Step1 Estimated total time needed for the testing
Estimated time required for testing | 30 | hours | include shaking + relocating shaker
Realistic estimatimation of required time | 60 | hours | * 2 for Try out + mistakes + DAQ malfunction + others
Total days of testing | 10 | days | 6 hours of vibration each day
Travel | 4 | days | 4 travel days to and from Austin + 4 * 0.5 days from site to site
weekends | 2 | days | UT personnel is required to take one day off for every 6 days
Days in the field | 16 | days
Step 2: Estimated equipment costs
T-Rex
Vibraton | 1260 | = Vibrator operating time * $21/hr (fuel cost only)
Tractor-Trailer
Highway | 3760 | = 1000 mile * 2 * $1.88 / mile ($1.00 overweight permit + $0.88fuel)
Fuel-Supply Pickup Truck |  | (fuel cost only)
Highway | 700 | = 1000 mile * 2 * $0.35 / mile (fuel cost only)
Recording equipment | 0 | free for NSF supported porject
Instrumentation Trailer | 0 | free for NSF supported porject
Total Equipment Cost: | 5720 | Account category: Material and supply
Step 3: Estimated travel costs
Per diem and hotel for 3 people | 8400 | = 3 people * days in the field * $175 /day / person
Airline tickets | 500 | = 1 person 1 trip
Rental van | 500
Equipment breakdown induced travel* |  | 20% of estimated user traveling cost should be prepared in user budget
NHERI-EF@UTexas can only cover equipment break-down induced travel costs
of the NHERI-EF@UTexas personnel.
Total Travel | 9400 | Account category: Travel
Step 4: Estimated other cost
Material and supply | 500
Mobile phone service in the field |  | no charge for NSF supported project
Site liability insurance**
Total Others | 500 | Account category: Material and supply
Step 5: Estimated total cost
Total direct cost | 15620
Indirect cost (58.5% overhead) | 9137.7 | Account category: Overhead
Total Cost | 24757.7
Notes:
* NHERI-EF@UTexas vibrators operate with pressures up to 4,000psi, and can output a ground force as high as 60,000 lbs. Components of the vehicle are under high pressure and strong vibration for a long period of time. From time to time, component can fail and field tests will be interrupted. Equipment repairing time ranges from 30 minutes to up to one month at a time. There is a limited amount of budget at NHERI-EF@UTexas to cover travel cost resulting from equipment breakdown and other incidents. However, this is for NHERI-EF@UTexas personnel and equipment only. Users are suggested to add an additional 20% of their traveling cost for unexpected equipment breakdown and other incidents.
** Users are required to conduct site survey. If they are required to purchase a site liability insurance policy, it is estimated to be about $3,000 per-project.
*** Field tests cannot be conducted over national holidays.

## Non- NSF Supported
Example Budget Sheet for a non-NSF Support Project
Note: Please add 58.55% overhead charge for the University of Texas at Austin
Last updated: December 15, 2020
Project description:
A NSF supported project using T-Rex and Instrumentation Van at a site 1000 miles from Austin for seismic prospecting study.
(700 miles + 300 miles from site to site (5 sites total))
Step1 Estimated total time needed for the testing
Estimated time required for testing | 30 | hours | include shaking + relocating shaker
Realistic estimatimation of required time | 60 | hours | * 2 for Try out + mistakes + DAQ malfunction + others
Total days of testing | 10 | days | 6 hours of vibration each day
Travel | 4 | days | 4 travel days to and from Austin + 4 * 0.5 days from site to site
weekends | 2 | days | UT personnel is required to take one day off for every 6 days
Days in the field | 16 | days
Step 2: Estimated equipment costs
T-Rex
Vibraton | 12840 | = Vibrator operating time * $214/hr
Tractor-Trailer (Big Rig)
Highway | 10000 | = 1000 mile * 2 * $5.00/ mile ($1.00 overweight permit + $4.00 per mile)
Fuel-Supply Pickup Truck
Highway | 1380 | = 1000 mile * 2 * $0.69 / mile (fuel cost only)
Recording equipment | 1156 | = 1 week * $289 per4-channel per week * 4 (16 channels total)
Instrumentation Trailer | 287 | $ 287 per project
Total Equipment Cost: | 25663 | Account category: Material and supply
Step 3: Estimated travel costs
Per diem and hotel for 3 people | 8400 | = 3 people * days in the field * $175 /day / person
Airline tickets | 500 | = 1 person 1 trip
Rental van | 500
Equipment breakdown induced travel* | 1880 | 20% of estimated traveling cost
Total Travel | 11280 | Account category: Travel
Step 4: Estimated other cost
Material and supply | 500
Mobile phone service in the field | 100
Site liability insurance** | 3000
Total Others | 3600 | Account category: Material and supply
Step 5: Estimate of personnel cost
2 Technicians | 40128 | = 2 people *(days in the field + 6 days of preparations) * 10hr/day
* $76/hr./person * 1.2 to account for overtime pay
1 Engineer | 32472 | = 1 person *(days in the field + 6 days of preparations) * 10hr/day
* $123/hr./person * 1.2 to account for overtime pay
Total Personnel | 72600 | Account category: Salary
Step 6: Estimated total cost
Total direct cost | 113143
Indirect cost (58.5% overhead) | 66188.655 | Account category: Overhead
Total Cost | 179331.655
Notes:
* NHERI-EF@UTexas vibrators operate with pressures up to 4,000psi, and can output a ground force as high as 60,000 lbs. Components of the vehicle are under high pressure and strong vibration for a long period of time. From time to time, component can fail and field tests will be interrupted. Equipment repairing time ranges from 30 minutes to up to one month at a time. An additional 20% of traveling cost is required for all field personnel for unexpected equipment breakdown and other incidents.
** Users are required to conduct site survey . The cost of the site liability insurance is estimated to be $3,000 per-project.
*** Field test cannot be conducted over national holidays.